## 1. Overview
ZUDOBOT SAAS — PROJECT PLAN (EXAMPLE)
Project | Zudobot SaaS Platform | Current Date | 2026-06-08
Platform | AI Sales Agent for Thai SMEs | Branch | zdbsandbox
Tech Stack | Next.js 14 · MongoDB · Gemini 2.5 · Google Auth | Version | v1.x → v2.0 GA
# | OBJECTIVE | KEY DELIVERABLE | STATUS
O1 | Production-ready AI sales agent platform for Thai SMEs | Zudobot SaaS v1.0 (web + API + widget) | In Progress
O2 | Tenant self-service onboarding with Google OAuth | Onboarding flow, dashboard, billing checkout | In Progress
O3 | Embeddable chat widget for client storefronts | widget.js with PDPA consent + product cards | Stabilising
O4 | Comply with Thai PDPA and GDPR | Data export, delete, consent audit trail | Done (Phase 2)
O5 | Launch monetisable ReadyPackage pricing system | CostPriceScenario + ReadyPackage + checkout | Done

## 2. Milestones
PHASE | MILESTONE | TARGET DATE | KEY DELIVERABLES | STATUS
Phase 1 | Core Platform | Jan 2026 | Next.js monorepo, MongoDB, Google Auth, Tenant dashboard, Bot config, Knowledge base, Widget v1 (text-only), Gemini 2.5, Landing page + /demo sandbox, Basic pricing section | DONE
Billing & Pricing | Pricing System | Mar 2026 | CostPriceScenario formula engine, ReadyPackage (dual-gate), /checkout?pkg= flow with VAT panel, Public pricing API with cache invalidation | DONE
Phase 2 | Feature Pack | May 2026 | PDPA Consent Form (widget + DB), Rich Product Cards, Deep Link Token (10-min / LINE Notify), Mobile dashboard + session timeout (30 min), GDPR export/delete + privacy page, 2FA TOTP + security page | DONE
Stabilisation | Quality Sprint | Jun 2026 | Zero TypeScript errors, Widget file attachment Hybrid A+B (≤5MB inline / >5MB Google Files API), Customer identity memory Tier 1/2/3, Constitutional AI Sections F + G, Human-like delay + typing indicator | IN PROGRESS
Phase 3 | Partner & Scale | Aug 2026 | Partner portal (Google Auth + commission), Deferred user creation (pending JWT), Admin monitoring side panel, Multi-language i18n (EN + TH) | PLANNED
Phase 4 | Growth & Analytics | Oct 2026 | Analytics dashboard (sessions / conversion / intent heatmap), A/B testing hooks for widget UI, Webhook integrations (LINE OA, Facebook Messenger), Enterprise tier + custom domain | PLANNED
v2.0 GA | General Availability Launch | Dec 2026 | All packages live on landing, Production hardening (rate limits, WAF, uptime SLA), Partner affiliate programme live | PLANNED

## 3. Roles
ROLE | RESPONSIBILITIES | OWNER (EXAMPLE) | PRIMARY APPS
Product Owner | Feature priorities, business decisions, ReadyPackage pricing rules, go/no-go for releases | Founder (Luesat) | All
Full-Stack Lead | Architecture, API design, code review, DB schema, CostPriceScenario engine | Senior Dev | apps/api, apps/web
Frontend Dev | Dashboard UI, landing page, checkout flow, admin panels, i18n | FE Dev | apps/web, apps/landing
Widget Engineer | packages/widget — file attachment, identity memory, animations, typing delay | Widget Specialist | packages/widget
AI / ML Engineer | Gemini prompt engineering, Constitutional AI rules (F+G), product embedding | AI Engineer | apps/api (Gemini layer)
QA Engineer | Manual + automated tests, mobile regression, PDPA consent validation, Deep Link tests | QA | All
DevOps | Amplify CI/CD, MongoDB Atlas, CDN for widget.js, env secrets injection | DevOps | Infra / CI
Legal / Compliance | PDPA/GDPR review, WHT accounting rules (backend-only), Terms of Service | Legal Advisor | Policy docs

## 4. Risk Register
# | RISK | LIKELIHOOD | IMPACT | MITIGATION STRATEGY | OWNER
R1 | Gemini API pricing change or quota limit | Medium | High | Cache responses, fallback prompt truncation, monitor token usage per tenant; set billing alerts on Google Cloud | AI Engineer + DevOps
R2 | PDPA non-compliance — consent not recorded | Low | Critical | Consent route records consentAt to DB; widget blocks all chat until consent stored in localStorage + DB confirmed | Full-Stack Lead + Legal
R3 | WHT shown to customers in checkout | Low | High | WHT is backend-only; checkout summary panel never renders WHT line; code review gate on checkout UI | Full-Stack Lead + Legal
R4 | Google OAuth token revoked mid-session | Medium | Medium | NextAuth session refresh every 15 min; graceful redirect to /login; preserve in-flight form data in sessionStorage | Full-Stack Lead
R5 | MongoDB Atlas outage | Low | Critical | Atlas multi-region replica set; read preference secondaryPreferred; automated backup every 6 h; health-check alert | DevOps
R6 | Widget script blocked by client CSP | Medium | Medium | Document required CSP headers in onboarding guide; provide nonce-compatible build option for enterprise clients | Widget Engineer
R7 | Competitor price undercut | Medium | Medium | ReadyPackage dual-gate (isActive + isOnSale) enables instant promo toggle without code deploy; CostPriceScenario keeps margin visible | Product Owner
R8 | Data breach — email hash or session token | Low | Critical | Store only SHA-256 hash (never raw email); rotate Deep Link tokens (10-min TTL); audit log on every GDPR delete | Full-Stack Lead + DevOps
R9 | Scope creep delaying GA launch | High | Medium | Strict phase gate: features not in approved phase backlog go to next sprint; PO has final say on mid-sprint additions | Product Owner
R10 | i18n mistranslation in Thai (legal text) | Medium | High | Native Thai speaker reviews all PDPA/consent copy before deploy; legal advisor signs off on privacy page wording | Legal + QA

## 5. Communication Plan
TYPE | CHANNEL | CADENCE | AUDIENCE | PURPOSE
INTERNAL | Daily Stand-up (LINE / Slack) | Daily 09:00 | All devs | Blockers, yesterday / today progress
INTERNAL | Sprint Review (Google Meet) | Bi-weekly (Friday) | All team + PO | Demo completed features, adjust backlog priority
INTERNAL | Architecture Decision (GitHub Discussion) | As needed | Tech leads | Record ADRs for major choices (DB schema, API contract, Gemini model version)
INTERNAL | Bug Triage (Linear) | Monday | QA + FE + BE | Prioritise regression bugs vs new feature work
INTERNAL | Finance / Pricing Review (Private doc) | Monthly | PO + Legal | CostPriceScenario updates, package margin review, WHT compliance check
INTERNAL | Security & Compliance Review | Quarterly | Full-Stack Lead + Legal + DevOps | PDPA audit trail check, 2FA adoption rate, token rotation review
EXTERNAL | Landing page /changelog | Per release | All users (public) | Feature announcements, pricing changes, new packages
EXTERNAL | LINE Notify alerts | On trigger | Tenant users | Live chat handoff notification, Deep Link token delivery
EXTERNAL | Email via Resend | On event | Registered tenants | Onboarding steps, billing receipts, renewal reminders, 2FA setup prompt
EXTERNAL | Partner Newsletter | Monthly | Active partners | Commission reports, new ReadyPackage availability, promo windows
EXTERNAL | Status Page | Continuous | All users | Uptime monitoring, planned maintenance windows, incident updates
EXTERNAL | In-widget admin broadcast | On admin push | Widget end-users (customers) | Feature highlights, promotions, store announcements
EXTERNAL | Support chat / email | On demand | Any user | Bug reports, billing questions, onboarding help

## 6. Feature Tracker
MODULE | FEATURE | PHASE | STATUS | APP / FILE | NOTES
Auth | Google OAuth (Tenant, Super Admin, Partner) | Phase 1 | DONE | apps/web — NextAuth | No email/password; Google Gmail only
Auth | 2FA TOTP Setup + Verify + Disable | Phase 2 | DONE | apps/web/app/api/tenant/2fa/* | RFC 6238, Web Crypto, QR code flow
Auth | Deferred user creation (pending JWT) | Phase 3 | PLANNED | apps/web — onboarding | User doc created only at onboarding completion
Widget | Text chat + Gemini 2.5 streaming | Phase 1 | DONE | packages/widget + apps/api
Widget | PDPA Consent Form | Phase 2 | DONE | packages/widget/src/Widget.ts | localStorage + DB consentAt record
Widget | Rich Product Cards | Phase 2 | DONE | packages/widget/src/Widget.ts | appendProductCards() — image, price, buy button
Widget | File Attachment Hybrid A+B | Stabilisation | IN PROGRESS | packages/widget + apps/web/api/widget/upload | ≤5MB inline base64, >5MB Google Files API
Widget | Customer Identity Memory Tier 1/2/3 | Stabilisation | IN PROGRESS | apps/web/app/api/widget/customer-memory | Email SHA-256 hash, never raw email
Widget | Human-like Delay + Typing Indicator | Stabilisation | IN PROGRESS | packages/widget/src/Widget.ts | chars × 0.044s, clamped 800–4500ms
Widget | Constitutional AI Section F (Identity) | Stabilisation | IN PROGRESS | apps/api — constitutionalRules.ts | F1–F5: consent, email rules
Widget | Constitutional AI Section G (Products) | Stabilisation | IN PROGRESS | apps/api — constitutionalRules.ts | G1–G5: topic detect, max 2 follow-ups
Pricing | CostPriceScenario formula engine | Billing Sprint | DONE | apps/web/app/api/admin/cost-price/* | G-multiplier, profit %, WHT backend-only
Pricing | ReadyPackage (isActive + isOnSale dual-gate) | Billing Sprint | DONE | apps/web/app/api/admin/ready-package/*
Pricing | /checkout?pkg= flow | Billing Sprint | DONE | apps/web/app/checkout/page.tsx | VAT shown, WHT never shown to customer
Pricing | Public pricing API + cache | Billing Sprint | DONE | apps/web/app/api/public/ready-packages | 1h cache, invalidated on admin save
Compliance | GDPR Data Export (JSON + CSV) | Phase 2 | DONE | apps/web/app/api/tenant/gdpr/export
Compliance | GDPR Data Delete (2-step confirm) | Phase 2 | DONE | apps/web/app/api/tenant/gdpr/delete | Phrase: DELETE_ALL_DATA
Live Chat | Deep Link Token (10-min TTL) | Phase 2 | DONE | apps/web/app/api/tenant/live-chat/* | LINE Notify includes token URL
Dashboard | Mobile layout + session timeout | Phase 2 | DONE | apps/web/app/dashboard/* | 25 min warning, 30 min auto-logout
Admin | Cost-Price admin UI with profit analysis | Billing Sprint | DONE | apps/web/app/admin/cost-price/* | 9-col table, search, keepPage pagination
Admin | Monitoring side panel (tenant details) | Billing Sprint | DONE | apps/web/app/admin/monitoring/* | Clickable rows → side panel
Partner | Partner portal + commission system | Phase 3 | PLANNED | TBD
Analytics | Session / conversion / intent dashboard | Phase 4 | PLANNED | TBD
Integrations | LINE OA + Facebook Messenger webhook | Phase 4 | PLANNED | TBD