## Gantt Timeline
ZUDOBOT SAAS — PROJECT PLAN & GANTT ¦ Jul 1 – Dec 31, 2026 ¦ Goal: Go-Live All Features in 6 Months
|  |  |  | July 2026 | [30 empty] | August 2026 | [30 empty] | September 2026 | [29 empty] | October 2026 | [30 empty] | November 2026 | [29 empty] | December 2026
|  |  |  | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th
Task / Feature | Type | Owner | Duration | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
PRE-PROJECT: REQUIREMENTS & PLANNING
Requirements Gathering | Analysis | BA + Stakeholders | 2 wks | bar: July 2026 We to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Th
Analysis + Backlog Creation | Analysis | BA + SA + Dev Lead | 2 wks | bar: July 2026 We to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Th
Spec / Non-Spec Documentation | Analysis | BA + Dev Team | 1 wk | bar: July 2026 We to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Th
MVP 1 — CORE AI & COMMERCE (Jul 22 – Sep 16)
▸ Sprint 1 ¦ 2 weeks (Jul 22 – Aug 4)
AI Chatbot Logic (Gemini 2.5 integration) | Development | AI Eng + Full-Stack | 2 wks | bar: July 2026 We to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Th
Widget Installation Logic | Development | Widget Engineer | 2 wks | bar: July 2026 We to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Th
Basic Chat UI (widget shell + open/close) | Development | FE Dev | 2 wks | bar: July 2026 We to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Th
▸ Sprint 2 ¦ 2 weeks (Aug 5 – Aug 18)
Main Package / Billing Setup | Development | Full-Stack Lead | 2 wks | bar: July 2026 We to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Th
ReadyPackage (isActive + isOnSale) | Development | Full-Stack Lead | 2 wks | bar: July 2026 We to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Th
Checkout Flow /checkout?pkg= | Development | FE Dev | 10 days | bar: July 2026 We to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Th
▸ Sprint 3 ¦ 2 weeks (Aug 19 – Sep 1)
Add-on Package | Development | Full-Stack Lead | 2 wks | bar: July 2026 We to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Th
CostPriceScenario Admin UI | Development | FE Dev | 2 wks | bar: July 2026 We to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Th
Tenant Dashboard Basics | Development | FE Dev | 1 wk | bar: July 2026 We to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Th
▸ QA TRACK — MVP 1 (parallel with dev)
QA: Create Test Cases (MVP 1) | QA / Test Case | QA + Tester | 6 wks | bar: July 2026 We to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Th
SIT (System Integration Test) | SIT | QA + Tester | 1 wk | bar: July 2026 We to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Th
UAT (Business User Testing) | UAT | BU User | 1 wk | bar: July 2026 We to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Th
★ UAT Sign-off — MVP 1 |  |  | 09-16 | bar: July 2026 We to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Th
MVP 2 — TENANT EXPERIENCE & COMPLIANCE (Sep 17 – Oct 29)
▸ Sprint 1 ¦ 2 weeks (Sep 17 – Sep 30)
PDPA Consent Form (widget + DB record) | Development | Widget Eng + Full-Stack | 2 wks | bar: July 2026 We to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Th
Rich Product Cards in widget | Development | Widget Engineer | 2 wks | bar: July 2026 We to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Th
Deep Link Token 10-min (LINE Notify) | Development | Full-Stack Lead | 1 wk | bar: July 2026 We to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Th
▸ Sprint 2 ¦ 2 weeks (Oct 1 – Oct 14)
GDPR Export / Delete (2-step confirm) | Development | Full-Stack Lead | 2 wks | bar: July 2026 We to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Th
2FA TOTP Setup + Verify + Disable | Development | Full-Stack Lead | 2 wks | bar: July 2026 We to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Th
Mobile Dashboard (responsive layout) | Development | FE Dev | 2 wks | bar: July 2026 We to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Th
Session Timeout (25 min warn / 30 auto) | Development | FE Dev | 1 wk | bar: July 2026 We to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Th
▸ QA TRACK — MVP 2 (parallel with dev)
QA: Create Test Cases (MVP 2) | QA / Test Case | QA + Tester | 4 wks | bar: July 2026 We to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Th
SIT (System Integration Test) | SIT | QA + Tester | 1 wk | bar: July 2026 We to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Th
UAT (Business User Testing) | UAT | BU User | 1 wk | bar: July 2026 We to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Th
★ UAT Sign-off — MVP 2 |  |  | 10-29 | bar: July 2026 We to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Th
MVP 3 — SCALE & PARTNER PROGRAMME (Oct 30 – Dec 11)
▸ Sprint 1 ¦ 2 weeks (Oct 30 – Nov 12)
Partner Portal + Google Auth | Development | Full-Stack Lead | 2 wks | bar: July 2026 We to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Th
File Attachment Hybrid A+B (≤5 / >5 MB) | Development | Widget Engineer | 2 wks | bar: July 2026 We to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Th
Customer Identity Memory (Tier 1/2/3) | Development | Widget Eng + AI Eng | 2 wks | bar: July 2026 We to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Th
▸ Sprint 2 ¦ 2 weeks (Nov 13 – Nov 26)
Analytics Dashboard (sessions/intent) | Development | FE Dev + AI Eng | 2 wks | bar: July 2026 We to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Th
LINE OA + FB Messenger Webhook | Development | Full-Stack Lead | 2 wks | bar: July 2026 We to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Th
Performance Hardening + Rate Limit/WAF | Development | DevOps | 1 wk | bar: July 2026 We to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Th
▸ QA TRACK — MVP 3 (parallel with dev)
QA: Create Test Cases (MVP 3) | QA / Test Case | QA + Tester | 4 wks | bar: July 2026 We to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Th
SIT (System Integration Test) | SIT | QA + Tester | 1 wk | bar: July 2026 We to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Th
UAT (Business User Testing) | UAT | BU User | 1 wk | bar: July 2026 We to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Th
★ UAT Sign-off — MVP 3 |  |  | 12-11 | bar: July 2026 We to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Th
GO-LIVE PREPARATION (Dec 12 – Dec 31)
Final Regression Test + Pen Test | QA / Test Case | QA + DevOps | 1 wk | bar: July 2026 We to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Th
Production Deploy + Monitoring Setup | Prep | DevOps | 1 wk | bar: July 2026 We to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Th
All Packages Live on Landing Page | Prep | FE Dev + Full-Stack | 3 days | bar: July 2026 We to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Th
★★ GO-LIVE — All Features |  |  | Dec 31 | bar: July 2026 We to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; July 2026 Mo to July 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to August 2026 Fr; August 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to September 2026 Fr; September 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; October 2026 Mo to October 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to November 2026 Fr; November 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Fr; December 2026 Mo to December 2026 Th

## Legend & Summary
ITEM | DESCRIPTION
COLOUR LEGEND
Requirements / Analysis | Pre-project requirements gathering and backlog creation
MVP 1 Development | Sprint 1–3 dev work: AI chatbot, widget, billing, add-on packages
MVP 2 Development | Sprint 1–2 dev work: consent, product cards, GDPR, 2FA, mobile
MVP 3 Development | Sprint 1–2 dev work: partner portal, file attach, analytics, webhooks
QA: Create Test Cases | QA runs parallel with dev — creating test cases throughout the sprint
SIT (System Integration) | System Integration Testing by QA + Tester after each MVP sprint
UAT (User Acceptance) | Business User Testing — BU User validates stories against requirements
Go-Live Prep | Final regression, production deploy, monitoring setup, go-live
Weekend (no work) | Saturdays and Sundays — no scheduled work
Milestone ★ | UAT Sign-off by BU Lead; marks completion of each MVP gate
GO-LIVE ★★ | All features live in production — Dec 31, 2026
MVP STRUCTURE OVERVIEW
PRE-PROJECT (Jul 1–21) | 2 weeks req gathering + 2 weeks BA analysis + spec/non-spec docs. BA consults dev team & SA to define backlog.
MVP 1 (Jul 22 – Sep 16) | Sprint 1: AI chatbot + widget install. Sprint 2: Main package / billing. Sprint 3: Add-on packages. QA parallel → SIT → UAT → Sign-off.
MVP 2 (Sep 17 – Oct 29) | Sprint 1: PDPA consent + product cards + deep link. Sprint 2: GDPR + 2FA + mobile + session timeout. QA parallel → SIT → UAT → Sign-off.
MVP 3 (Oct 30 – Dec 11) | Sprint 1: Partner portal + file attach + identity memory. Sprint 2: Analytics + webhooks + hardening. QA parallel → SIT → UAT → Sign-off.
GO-LIVE PREP (Dec 12–31) | Final regression + pen test. Production deploy. All packages live. GO-LIVE Dec 31, 2026.

## Objectives
# | Objective | Key Deliverable | MVP Gate | Status
O1 | Production-ready AI sales agent platform for Thai SMEs | Zudobot SaaS web + API + widget (end-to-end) | MVP 1 | Planned
O2 | Embeddable widget that installs in one script line | packages/widget — one <script> tag, tenant ID | MVP 1 | Planned
O3 | Billing: Main Package + Add-on Package checkout | /checkout?pkg= flow, ReadyPackage, VAT summary panel | MVP 1 | Planned
O4 | PDPA-compliant consent + Rich Product Cards in widget | Consent stored to DB; product card UI in chat | MVP 2 | Planned
O5 | Full GDPR compliance (export, delete, 2FA) | Privacy page, GDPR API, 2FA TOTP, security page | MVP 2 | Planned
O6 | Partner portal with commission programme | Partner Google Auth, earn-rate config, referral tracking | MVP 3 | Planned
O7 | Analytics + third-party integrations | Session/intent dashboard, LINE OA, Facebook Messenger | MVP 3 | Planned
O8 | Production go-live for all features within 6 months | All features live, monitoring, SLA in place | Go-Live | Planned

## Roles
Role | Responsibilities | Owner (Example) | Involved In
Product Owner | Feature priorities, MVP gate decisions, ReadyPackage pricing rules, go/no-go for releases | Founder (Luesat) | All phases
Business Analyst (BA) | Gather requirements, create backlog, write spec & non-spec docs, consult dev & SA on stories | BA Lead | Pre-project
Solution Architect (SA) | Review BA spec, define API contracts, DB schema, integration patterns | SA | Pre-project + Dev
Full-Stack Lead | Architecture, API routes, DB models, CostPriceScenario engine, auth, billing, partner system | Senior Dev | MVP 1-3
Frontend Dev | Dashboard UI, landing page, checkout flow, admin panels, i18n (EN+TH), analytics screens | FE Dev | MVP 1-3
Widget Engineer | packages/widget — install logic, product cards, file attachment, identity memory, typing delay | Widget Specialist | MVP 1 + MVP 3
AI / ML Engineer | Gemini prompt engineering, Constitutional AI rules (F+G), intent detection, embedding | AI Engineer | MVP 1 + MVP 3
QA / Tester | Create test cases (parallel with dev), execute SIT, raise defects, re-test fixes | QA + Tester | All MVPs
BU User | Execute UAT against acceptance criteria, raise issues to BU Lead, validate fixed defects | Business User | UAT per MVP
BU Lead | Review UAT results, approve UAT sign-off, sign off go-live readiness | BU Lead / PM | UAT Sign-off
DevOps | Amplify CI/CD, MongoDB Atlas, CDN for widget.js, env secrets, WAF, uptime monitoring | DevOps | MVP 1 + Go-Live
Legal / Compliance | PDPA/GDPR review, WHT accounting rules (backend-only), Terms of Service copy | Legal Advisor | Pre-project + MVP 2

## Risk Register
# | Risk | Likelihood | Impact | Mitigation Strategy | Owner
R1 | Requirement changes after backlog sign-off | High | High | Change control process: all changes logged, impact assessed by BA+SA, re-scoped into next MVP sprint | BA + PO
R2 | UAT not signed-off on time → delays go-live | Medium | Critical | Weekly UAT status check with BU Lead; escalation path to PO if >3 open blockers by UAT Day 4 | BU Lead + PM
R3 | Gemini API quota limit reached under load | Medium | High | Cache responses; token-budget per tenant; alert at 80% quota; fallback prompt truncation | AI Eng + DevOps
R4 | PDPA non-compliance — consent not recorded | Low | Critical | Widget blocks chat until consentAt written to DB; automated PDPA test in SIT suite | Full-Stack + Legal
R5 | WHT accidentally shown in checkout UI | Low | High | WHT is backend-only; UI code-review gate; SIT test case validates WHT never appears in browser | Full-Stack + Legal
R6 | Sprint velocity lower than estimated | Medium | High | Buffer sprints built in; de-scope non-critical stories to next MVP; daily stand-up tracks blockers | Full-Stack Lead + PO
R7 | MongoDB Atlas outage mid-sprint | Low | Critical | Multi-region replica set; 6h backup; read preference secondaryPreferred; alert to DevOps on-call | DevOps
R8 | Data breach — session token or email hash | Low | Critical | SHA-256 hash only; 10-min Deep Link TTL; audit log on GDPR delete; pen test in go-live prep | Full-Stack + DevOps
R9 | Partner commission formula disputed post-launch | Medium | Medium | Legal sign-off on commission rules before MVP 3 development starts | PO + Legal
R10 | Key developer unavailable (sick/leave) | Medium | High | Cross-training between Widget Eng and FE Dev; architecture docs kept up-to-date by SA | Full-Stack Lead

## Communication Plan
Type | Channel | Cadence | Audience | Purpose
INTERNAL | Daily Stand-up (LINE / Slack) | Daily 09:00 | All devs + QA | Blockers, yesterday/today progress, sprint burn-down check
INTERNAL | Sprint Planning (Google Meet) | Start of each sprint | Dev + QA + BA + PO | Pick stories from backlog, estimate points, set sprint goal
INTERNAL | Sprint Review / Demo | End of each sprint (bi-weekly) | All team + PO + BU Lead | Demo completed features, accept/reject stories, update backlog
INTERNAL | Sprint Retrospective | After each review | Dev + QA | What went well, what to improve, action items
INTERNAL | BA Spec Review (GitHub / Confluence) | As needed | BA + SA + Dev Lead | Clarify spec & non-spec requirements before dev starts a story
INTERNAL | Architecture Decision Records (GitHub) | As needed | SA + Tech leads | Document ADRs: DB schema, API contract, Gemini model version
INTERNAL | Bug Triage (Linear / Jira) | Monday | QA + FE + BE | Prioritise SIT defects vs feature work; assign owners
INTERNAL | UAT Readiness Review | Before each UAT starts | PM + QA + BU Lead | Confirm SIT pass rate, open blockers, UAT environment ready
INTERNAL | Finance / Pricing Review | Monthly | PO + Legal | CostPriceScenario margin, WHT compliance, package pricing sign-off
EXTERNAL | Landing page /changelog | Per release / MVP gate | All users (public) | Feature announcements, pricing changes, new packages
EXTERNAL | LINE Notify Alerts | On trigger (live chat) | Tenant users | Live chat handoff notification + 10-min Deep Link token
EXTERNAL | Email via Resend | On event | Registered tenants | Onboarding, billing receipts, renewal, 2FA setup prompt
EXTERNAL | Partner Newsletter | Monthly | Active partners | Commission reports, new ReadyPackage, promo windows
EXTERNAL | Status Page | Continuous | All users | Uptime, planned maintenance windows, incident updates
EXTERNAL | UAT Invite + Sign-off Email | Per MVP UAT cycle | BU User + BU Lead | UAT start notification, test scope, sign-off confirmation
EXTERNAL | Go-Live Announcement (email + landing) | Dec 31, 2026 | All users + partners | Official launch of all features, new pricing, partner programme live