## Gantt Timeline
Task / Feature | Phase | Owner | Status | June 2026 | [29 empty] | July 2026 | [30 empty] | August 2026 | [30 empty] | September 2026 | [29 empty] | October 2026 | [30 empty] | November 2026 | [29 empty] | December 2026
|  |  |  | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
── STABILISATION SPRINT (Jun 2026)
Widget: File Attachment Hybrid A+B | Stabilisation | Widget Eng | In Progress | bar: June 2026 Mo 1 to June 2026 Fr 5; June 2026 Tu 9 to June 2026 Fr 12; June 2026 Mo 15 to June 2026 Fr 19; June 2026 Mo 22 to June 2026 Fr 26; June 2026 Mo 29 to July 2026 Fr 3; July 2026 Mo 6 to July 2026 Fr 10; July 2026 Mo 13 to July 2026 Fr 17; July 2026 Mo 20 to July 2026 Fr 24; July 2026 Mo 27 to July 2026 Fr 31; August 2026 Mo 3 to August 2026 Fr 7; August 2026 Mo 10 to August 2026 Fr 14; August 2026 Mo 17 to August 2026 Fr 21; August 2026 Mo 24 to August 2026 Fr 28; August 2026 Mo 31 to September 2026 Fr 4; September 2026 Mo 7 to September 2026 Fr 11; September 2026 Mo 14 to September 2026 Fr 18; September 2026 Mo 21 to September 2026 Fr 25; September 2026 Mo 28 to October 2026 Fr 2; October 2026 Mo 5 to October 2026 Fr 9; October 2026 Mo 12 to October 2026 Fr 16; October 2026 Mo 19 to October 2026 Fr 23; October 2026 Mo 26 to October 2026 Fr 30; November 2026 Mo 2 to November 2026 Fr 6; November 2026 Mo 9 to November 2026 Fr 13; November 2026 Mo 16 to November 2026 Fr 20; November 2026 Mo 23 to November 2026 Fr 27; November 2026 Mo 30 to December 2026 Fr 4; December 2026 Mo 7 to December 2026 Fr 11; December 2026 Mo 14 to December 2026 Fr 18; December 2026 Mo 21 to December 2026 Fr 25; December 2026 Mo 28 to December 2026 Th 31
Widget: Customer Identity Tier 1/2/3 | Stabilisation | Widget Eng | In Progress | bar: June 2026 Mo 1 to June 2026 Fr 5; June 2026 Tu 9 to June 2026 Fr 12; June 2026 Mo 15 to June 2026 Fr 19; June 2026 Mo 22 to June 2026 Fr 26; June 2026 Mo 29 to July 2026 Fr 3; July 2026 Mo 6 to July 2026 Fr 10; July 2026 Mo 13 to July 2026 Fr 17; July 2026 Mo 20 to July 2026 Fr 24; July 2026 Mo 27 to July 2026 Fr 31; August 2026 Mo 3 to August 2026 Fr 7; August 2026 Mo 10 to August 2026 Fr 14; August 2026 Mo 17 to August 2026 Fr 21; August 2026 Mo 24 to August 2026 Fr 28; August 2026 Mo 31 to September 2026 Fr 4; September 2026 Mo 7 to September 2026 Fr 11; September 2026 Mo 14 to September 2026 Fr 18; September 2026 Mo 21 to September 2026 Fr 25; September 2026 Mo 28 to October 2026 Fr 2; October 2026 Mo 5 to October 2026 Fr 9; October 2026 Mo 12 to October 2026 Fr 16; October 2026 Mo 19 to October 2026 Fr 23; October 2026 Mo 26 to October 2026 Fr 30; November 2026 Mo 2 to November 2026 Fr 6; November 2026 Mo 9 to November 2026 Fr 13; November 2026 Mo 16 to November 2026 Fr 20; November 2026 Mo 23 to November 2026 Fr 27; November 2026 Mo 30 to December 2026 Fr 4; December 2026 Mo 7 to December 2026 Fr 11; December 2026 Mo 14 to December 2026 Fr 18; December 2026 Mo 21 to December 2026 Fr 25; December 2026 Mo 28 to December 2026 Th 31
Widget: Human-like Delay + Typing | Stabilisation | Widget Eng | In Progress | bar: June 2026 Mo 1 to June 2026 Fr 5; June 2026 Tu 9 to June 2026 Fr 12; June 2026 Mo 15 to June 2026 Fr 19; June 2026 Mo 22 to June 2026 Fr 26; June 2026 Mo 29 to July 2026 Fr 3; July 2026 Mo 6 to July 2026 Fr 10; July 2026 Mo 13 to July 2026 Fr 17; July 2026 Mo 20 to July 2026 Fr 24; July 2026 Mo 27 to July 2026 Fr 31; August 2026 Mo 3 to August 2026 Fr 7; August 2026 Mo 10 to August 2026 Fr 14; August 2026 Mo 17 to August 2026 Fr 21; August 2026 Mo 24 to August 2026 Fr 28; August 2026 Mo 31 to September 2026 Fr 4; September 2026 Mo 7 to September 2026 Fr 11; September 2026 Mo 14 to September 2026 Fr 18; September 2026 Mo 21 to September 2026 Fr 25; September 2026 Mo 28 to October 2026 Fr 2; October 2026 Mo 5 to October 2026 Fr 9; October 2026 Mo 12 to October 2026 Fr 16; October 2026 Mo 19 to October 2026 Fr 23; October 2026 Mo 26 to October 2026 Fr 30; November 2026 Mo 2 to November 2026 Fr 6; November 2026 Mo 9 to November 2026 Fr 13; November 2026 Mo 16 to November 2026 Fr 20; November 2026 Mo 23 to November 2026 Fr 27; November 2026 Mo 30 to December 2026 Fr 4; December 2026 Mo 7 to December 2026 Fr 11; December 2026 Mo 14 to December 2026 Fr 18; December 2026 Mo 21 to December 2026 Fr 25; December 2026 Mo 28 to December 2026 Th 31
Constitutional AI — Section F | Stabilisation | AI Engineer | In Progress | bar: June 2026 Mo 1 to June 2026 Fr 5; June 2026 Tu 9 to June 2026 Fr 12; June 2026 Mo 15 to June 2026 Fr 19; June 2026 Mo 22 to June 2026 Fr 26; June 2026 Mo 29 to July 2026 Fr 3; July 2026 Mo 6 to July 2026 Fr 10; July 2026 Mo 13 to July 2026 Fr 17; July 2026 Mo 20 to July 2026 Fr 24; July 2026 Mo 27 to July 2026 Fr 31; August 2026 Mo 3 to August 2026 Fr 7; August 2026 Mo 10 to August 2026 Fr 14; August 2026 Mo 17 to August 2026 Fr 21; August 2026 Mo 24 to August 2026 Fr 28; August 2026 Mo 31 to September 2026 Fr 4; September 2026 Mo 7 to September 2026 Fr 11; September 2026 Mo 14 to September 2026 Fr 18; September 2026 Mo 21 to September 2026 Fr 25; September 2026 Mo 28 to October 2026 Fr 2; October 2026 Mo 5 to October 2026 Fr 9; October 2026 Mo 12 to October 2026 Fr 16; October 2026 Mo 19 to October 2026 Fr 23; October 2026 Mo 26 to October 2026 Fr 30; November 2026 Mo 2 to November 2026 Fr 6; November 2026 Mo 9 to November 2026 Fr 13; November 2026 Mo 16 to November 2026 Fr 20; November 2026 Mo 23 to November 2026 Fr 27; November 2026 Mo 30 to December 2026 Fr 4; December 2026 Mo 7 to December 2026 Fr 11; December 2026 Mo 14 to December 2026 Fr 18; December 2026 Mo 21 to December 2026 Fr 25; December 2026 Mo 28 to December 2026 Th 31
Constitutional AI — Section G | Stabilisation | AI Engineer | In Progress | bar: June 2026 Mo 1 to June 2026 Fr 5; June 2026 Tu 9 to June 2026 Fr 12; June 2026 Mo 15 to June 2026 Fr 19; June 2026 Mo 22 to June 2026 Fr 26; June 2026 Mo 29 to July 2026 Fr 3; July 2026 Mo 6 to July 2026 Fr 10; July 2026 Mo 13 to July 2026 Fr 17; July 2026 Mo 20 to July 2026 Fr 24; July 2026 Mo 27 to July 2026 Fr 31; August 2026 Mo 3 to August 2026 Fr 7; August 2026 Mo 10 to August 2026 Fr 14; August 2026 Mo 17 to August 2026 Fr 21; August 2026 Mo 24 to August 2026 Fr 28; August 2026 Mo 31 to September 2026 Fr 4; September 2026 Mo 7 to September 2026 Fr 11; September 2026 Mo 14 to September 2026 Fr 18; September 2026 Mo 21 to September 2026 Fr 25; September 2026 Mo 28 to October 2026 Fr 2; October 2026 Mo 5 to October 2026 Fr 9; October 2026 Mo 12 to October 2026 Fr 16; October 2026 Mo 19 to October 2026 Fr 23; October 2026 Mo 26 to October 2026 Fr 30; November 2026 Mo 2 to November 2026 Fr 6; November 2026 Mo 9 to November 2026 Fr 13; November 2026 Mo 16 to November 2026 Fr 20; November 2026 Mo 23 to November 2026 Fr 27; November 2026 Mo 30 to December 2026 Fr 4; December 2026 Mo 7 to December 2026 Fr 11; December 2026 Mo 14 to December 2026 Fr 18; December 2026 Mo 21 to December 2026 Fr 25; December 2026 Mo 28 to December 2026 Th 31
TypeScript clean build (zero errors) | Stabilisation | Full-Stack Lead | In Progress | bar: June 2026 Mo 1 to June 2026 Fr 5; June 2026 Tu 9 to June 2026 Fr 12; June 2026 Mo 15 to June 2026 Fr 19; June 2026 Mo 22 to June 2026 Fr 26; June 2026 Mo 29 to July 2026 Fr 3; July 2026 Mo 6 to July 2026 Fr 10; July 2026 Mo 13 to July 2026 Fr 17; July 2026 Mo 20 to July 2026 Fr 24; July 2026 Mo 27 to July 2026 Fr 31; August 2026 Mo 3 to August 2026 Fr 7; August 2026 Mo 10 to August 2026 Fr 14; August 2026 Mo 17 to August 2026 Fr 21; August 2026 Mo 24 to August 2026 Fr 28; August 2026 Mo 31 to September 2026 Fr 4; September 2026 Mo 7 to September 2026 Fr 11; September 2026 Mo 14 to September 2026 Fr 18; September 2026 Mo 21 to September 2026 Fr 25; September 2026 Mo 28 to October 2026 Fr 2; October 2026 Mo 5 to October 2026 Fr 9; October 2026 Mo 12 to October 2026 Fr 16; October 2026 Mo 19 to October 2026 Fr 23; October 2026 Mo 26 to October 2026 Fr 30; November 2026 Mo 2 to November 2026 Fr 6; November 2026 Mo 9 to November 2026 Fr 13; November 2026 Mo 16 to November 2026 Fr 20; November 2026 Mo 23 to November 2026 Fr 27; November 2026 Mo 30 to December 2026 Fr 4; December 2026 Mo 7 to December 2026 Fr 11; December 2026 Mo 14 to December 2026 Fr 18; December 2026 Mo 21 to December 2026 Fr 25; December 2026 Mo 28 to December 2026 Th 31
QA regression + mobile test | Stabilisation | QA | In Progress | bar: June 2026 Mo 1 to June 2026 Fr 5; June 2026 Tu 9 to June 2026 Fr 12; June 2026 Mo 15 to June 2026 Fr 19; June 2026 Mo 22 to June 2026 Fr 26; June 2026 Mo 29 to July 2026 Fr 3; July 2026 Mo 6 to July 2026 Fr 10; July 2026 Mo 13 to July 2026 Fr 17; July 2026 Mo 20 to July 2026 Fr 24; July 2026 Mo 27 to July 2026 Fr 31; August 2026 Mo 3 to August 2026 Fr 7; August 2026 Mo 10 to August 2026 Fr 14; August 2026 Mo 17 to August 2026 Fr 21; August 2026 Mo 24 to August 2026 Fr 28; August 2026 Mo 31 to September 2026 Fr 4; September 2026 Mo 7 to September 2026 Fr 11; September 2026 Mo 14 to September 2026 Fr 18; September 2026 Mo 21 to September 2026 Fr 25; September 2026 Mo 28 to October 2026 Fr 2; October 2026 Mo 5 to October 2026 Fr 9; October 2026 Mo 12 to October 2026 Fr 16; October 2026 Mo 19 to October 2026 Fr 23; October 2026 Mo 26 to October 2026 Fr 30; November 2026 Mo 2 to November 2026 Fr 6; November 2026 Mo 9 to November 2026 Fr 13; November 2026 Mo 16 to November 2026 Fr 20; November 2026 Mo 23 to November 2026 Fr 27; November 2026 Mo 30 to December 2026 Fr 4; December 2026 Mo 7 to December 2026 Fr 11; December 2026 Mo 14 to December 2026 Fr 18; December 2026 Mo 21 to December 2026 Fr 25; December 2026 Mo 28 to December 2026 Th 31
★ Stabilisation Complete |  |  | Jun 28 | bar: June 2026 Mo 1 to June 2026 Fr 5; June 2026 Tu 9 to June 2026 Fr 12; June 2026 Mo 15 to June 2026 Fr 19; June 2026 Mo 22 to June 2026 Fr 26; June 2026 Su 28 to July 2026 Fr 3; July 2026 Mo 6 to July 2026 Fr 10; July 2026 Mo 13 to July 2026 Fr 17; July 2026 Mo 20 to July 2026 Fr 24; July 2026 Mo 27 to July 2026 Fr 31; August 2026 Mo 3 to August 2026 Fr 7; August 2026 Mo 10 to August 2026 Fr 14; August 2026 Mo 17 to August 2026 Fr 21; August 2026 Mo 24 to August 2026 Fr 28; August 2026 Mo 31 to September 2026 Fr 4; September 2026 Mo 7 to September 2026 Fr 11; September 2026 Mo 14 to September 2026 Fr 18; September 2026 Mo 21 to September 2026 Fr 25; September 2026 Mo 28 to October 2026 Fr 2; October 2026 Mo 5 to October 2026 Fr 9; October 2026 Mo 12 to October 2026 Fr 16; October 2026 Mo 19 to October 2026 Fr 23; October 2026 Mo 26 to October 2026 Fr 30; November 2026 Mo 2 to November 2026 Fr 6; November 2026 Mo 9 to November 2026 Fr 13; November 2026 Mo 16 to November 2026 Fr 20; November 2026 Mo 23 to November 2026 Fr 27; November 2026 Mo 30 to December 2026 Fr 4; December 2026 Mo 7 to December 2026 Fr 11; December 2026 Mo 14 to December 2026 Fr 18; December 2026 Mo 21 to December 2026 Fr 25; December 2026 Mo 28 to December 2026 Th 31
── PHASE 3 — PARTNER & SCALE
Partner Portal — Google Auth flow | Phase 3 | Full-Stack Lead | Planned | bar: June 2026 Mo 1 to June 2026 Fr 5; June 2026 Tu 9 to June 2026 Fr 12; June 2026 Mo 15 to June 2026 Fr 19; June 2026 Mo 22 to June 2026 Fr 26; June 2026 Mo 29 to July 2026 Fr 3; July 2026 Mo 6 to July 2026 Fr 10; July 2026 Mo 13 to July 2026 Fr 17; July 2026 Mo 20 to July 2026 Fr 24; July 2026 Mo 27 to July 2026 Fr 31; August 2026 Mo 3 to August 2026 Fr 7; August 2026 Mo 10 to August 2026 Fr 14; August 2026 Mo 17 to August 2026 Fr 21; August 2026 Mo 24 to August 2026 Fr 28; August 2026 Mo 31 to September 2026 Fr 4; September 2026 Mo 7 to September 2026 Fr 11; September 2026 Mo 14 to September 2026 Fr 18; September 2026 Mo 21 to September 2026 Fr 25; September 2026 Mo 28 to October 2026 Fr 2; October 2026 Mo 5 to October 2026 Fr 9; October 2026 Mo 12 to October 2026 Fr 16; October 2026 Mo 19 to October 2026 Fr 23; October 2026 Mo 26 to October 2026 Fr 30; November 2026 Mo 2 to November 2026 Fr 6; November 2026 Mo 9 to November 2026 Fr 13; November 2026 Mo 16 to November 2026 Fr 20; November 2026 Mo 23 to November 2026 Fr 27; November 2026 Mo 30 to December 2026 Fr 4; December 2026 Mo 7 to December 2026 Fr 11; December 2026 Mo 14 to December 2026 Fr 18; December 2026 Mo 21 to December 2026 Fr 25; December 2026 Mo 28 to December 2026 Th 31
Partner commission & referral system | Phase 3 | Full-Stack Lead | Planned | bar: June 2026 Mo 1 to June 2026 Fr 5; June 2026 Tu 9 to June 2026 Fr 12; June 2026 Mo 15 to June 2026 Fr 19; June 2026 Mo 22 to June 2026 Fr 26; June 2026 Mo 29 to July 2026 Fr 3; July 2026 Mo 6 to July 2026 Fr 10; July 2026 Mo 13 to July 2026 Fr 17; July 2026 Mo 20 to July 2026 Fr 24; July 2026 Mo 27 to July 2026 Fr 31; August 2026 Mo 3 to August 2026 Fr 7; August 2026 Mo 10 to August 2026 Fr 14; August 2026 Mo 17 to August 2026 Fr 21; August 2026 Mo 24 to August 2026 Fr 28; August 2026 Mo 31 to September 2026 Fr 4; September 2026 Mo 7 to September 2026 Fr 11; September 2026 Mo 14 to September 2026 Fr 18; September 2026 Mo 21 to September 2026 Fr 25; September 2026 Mo 28 to October 2026 Fr 2; October 2026 Mo 5 to October 2026 Fr 9; October 2026 Mo 12 to October 2026 Fr 16; October 2026 Mo 19 to October 2026 Fr 23; October 2026 Mo 26 to October 2026 Fr 30; November 2026 Mo 2 to November 2026 Fr 6; November 2026 Mo 9 to November 2026 Fr 13; November 2026 Mo 16 to November 2026 Fr 20; November 2026 Mo 23 to November 2026 Fr 27; November 2026 Mo 30 to December 2026 Fr 4; December 2026 Mo 7 to December 2026 Fr 11; December 2026 Mo 14 to December 2026 Fr 18; December 2026 Mo 21 to December 2026 Fr 25; December 2026 Mo 28 to December 2026 Th 31
Deferred user creation (pending JWT) | Phase 3 | Full-Stack Lead | Planned | bar: June 2026 Mo 1 to June 2026 Fr 5; June 2026 Tu 9 to June 2026 Fr 12; June 2026 Mo 15 to June 2026 Fr 19; June 2026 Mo 22 to June 2026 Fr 26; June 2026 Mo 29 to July 2026 Fr 3; July 2026 Mo 6 to July 2026 Fr 10; July 2026 Mo 13 to July 2026 Fr 17; July 2026 Mo 20 to July 2026 Fr 24; July 2026 Mo 27 to July 2026 Fr 31; August 2026 Mo 3 to August 2026 Fr 7; August 2026 Mo 10 to August 2026 Fr 14; August 2026 Mo 17 to August 2026 Fr 21; August 2026 Mo 24 to August 2026 Fr 28; August 2026 Mo 31 to September 2026 Fr 4; September 2026 Mo 7 to September 2026 Fr 11; September 2026 Mo 14 to September 2026 Fr 18; September 2026 Mo 21 to September 2026 Fr 25; September 2026 Mo 28 to October 2026 Fr 2; October 2026 Mo 5 to October 2026 Fr 9; October 2026 Mo 12 to October 2026 Fr 16; October 2026 Mo 19 to October 2026 Fr 23; October 2026 Mo 26 to October 2026 Fr 30; November 2026 Mo 2 to November 2026 Fr 6; November 2026 Mo 9 to November 2026 Fr 13; November 2026 Mo 16 to November 2026 Fr 20; November 2026 Mo 23 to November 2026 Fr 27; November 2026 Mo 30 to December 2026 Fr 4; December 2026 Mo 7 to December 2026 Fr 11; December 2026 Mo 14 to December 2026 Fr 18; December 2026 Mo 21 to December 2026 Fr 25; December 2026 Mo 28 to December 2026 Th 31
Admin monitoring side panel | Phase 3 | FE Dev | Planned | bar: June 2026 Mo 1 to June 2026 Fr 5; June 2026 Tu 9 to June 2026 Fr 12; June 2026 Mo 15 to June 2026 Fr 19; June 2026 Mo 22 to June 2026 Fr 26; June 2026 Mo 29 to July 2026 Fr 3; July 2026 Mo 6 to July 2026 Fr 10; July 2026 Mo 13 to July 2026 Fr 17; July 2026 Mo 20 to July 2026 Fr 24; July 2026 Mo 27 to July 2026 Fr 31; August 2026 Mo 3 to August 2026 Fr 7; August 2026 Mo 10 to August 2026 Fr 14; August 2026 Mo 17 to August 2026 Fr 21; August 2026 Mo 24 to August 2026 Fr 28; August 2026 Mo 31 to September 2026 Fr 4; September 2026 Mo 7 to September 2026 Fr 11; September 2026 Mo 14 to September 2026 Fr 18; September 2026 Mo 21 to September 2026 Fr 25; September 2026 Mo 28 to October 2026 Fr 2; October 2026 Mo 5 to October 2026 Fr 9; October 2026 Mo 12 to October 2026 Fr 16; October 2026 Mo 19 to October 2026 Fr 23; October 2026 Mo 26 to October 2026 Fr 30; November 2026 Mo 2 to November 2026 Fr 6; November 2026 Mo 9 to November 2026 Fr 13; November 2026 Mo 16 to November 2026 Fr 20; November 2026 Mo 23 to November 2026 Fr 27; November 2026 Mo 30 to December 2026 Fr 4; December 2026 Mo 7 to December 2026 Fr 11; December 2026 Mo 14 to December 2026 Fr 18; December 2026 Mo 21 to December 2026 Fr 25; December 2026 Mo 28 to December 2026 Th 31
Multi-language i18n (EN + TH) | Phase 3 | FE Dev | Planned | bar: June 2026 Mo 1 to June 2026 Fr 5; June 2026 Tu 9 to June 2026 Fr 12; June 2026 Mo 15 to June 2026 Fr 19; June 2026 Mo 22 to June 2026 Fr 26; June 2026 Mo 29 to July 2026 Fr 3; July 2026 Mo 6 to July 2026 Fr 10; July 2026 Mo 13 to July 2026 Fr 17; July 2026 Mo 20 to July 2026 Fr 24; July 2026 Mo 27 to July 2026 Fr 31; August 2026 Mo 3 to August 2026 Fr 7; August 2026 Mo 10 to August 2026 Fr 14; August 2026 Mo 17 to August 2026 Fr 21; August 2026 Mo 24 to August 2026 Fr 28; August 2026 Mo 31 to September 2026 Fr 4; September 2026 Mo 7 to September 2026 Fr 11; September 2026 Mo 14 to September 2026 Fr 18; September 2026 Mo 21 to September 2026 Fr 25; September 2026 Mo 28 to October 2026 Fr 2; October 2026 Mo 5 to October 2026 Fr 9; October 2026 Mo 12 to October 2026 Fr 16; October 2026 Mo 19 to October 2026 Fr 23; October 2026 Mo 26 to October 2026 Fr 30; November 2026 Mo 2 to November 2026 Fr 6; November 2026 Mo 9 to November 2026 Fr 13; November 2026 Mo 16 to November 2026 Fr 20; November 2026 Mo 23 to November 2026 Fr 27; November 2026 Mo 30 to December 2026 Fr 4; December 2026 Mo 7 to December 2026 Fr 11; December 2026 Mo 14 to December 2026 Fr 18; December 2026 Mo 21 to December 2026 Fr 25; December 2026 Mo 28 to December 2026 Th 31
Phase 3 QA + UAT | Phase 3 | QA | Planned | bar: June 2026 Mo 1 to June 2026 Fr 5; June 2026 Tu 9 to June 2026 Fr 12; June 2026 Mo 15 to June 2026 Fr 19; June 2026 Mo 22 to June 2026 Fr 26; June 2026 Mo 29 to July 2026 Fr 3; July 2026 Mo 6 to July 2026 Fr 10; July 2026 Mo 13 to July 2026 Fr 17; July 2026 Mo 20 to July 2026 Fr 24; July 2026 Mo 27 to July 2026 Fr 31; August 2026 Mo 3 to August 2026 Fr 7; August 2026 Mo 10 to August 2026 Fr 14; August 2026 Mo 17 to August 2026 Fr 21; August 2026 Mo 24 to August 2026 Fr 28; August 2026 Mo 31 to September 2026 Fr 4; September 2026 Mo 7 to September 2026 Fr 11; September 2026 Mo 14 to September 2026 Fr 18; September 2026 Mo 21 to September 2026 Fr 25; September 2026 Mo 28 to October 2026 Fr 2; October 2026 Mo 5 to October 2026 Fr 9; October 2026 Mo 12 to October 2026 Fr 16; October 2026 Mo 19 to October 2026 Fr 23; October 2026 Mo 26 to October 2026 Fr 30; November 2026 Mo 2 to November 2026 Fr 6; November 2026 Mo 9 to November 2026 Fr 13; November 2026 Mo 16 to November 2026 Fr 20; November 2026 Mo 23 to November 2026 Fr 27; November 2026 Mo 30 to December 2026 Fr 4; December 2026 Mo 7 to December 2026 Fr 11; December 2026 Mo 14 to December 2026 Fr 18; December 2026 Mo 21 to December 2026 Fr 25; December 2026 Mo 28 to December 2026 Th 31
★ Phase 3 Milestone |  |  | Aug 22 | bar: June 2026 Mo 1 to June 2026 Fr 5; June 2026 Tu 9 to June 2026 Fr 12; June 2026 Mo 15 to June 2026 Fr 19; June 2026 Mo 22 to June 2026 Fr 26; June 2026 Mo 29 to July 2026 Fr 3; July 2026 Mo 6 to July 2026 Fr 10; July 2026 Mo 13 to July 2026 Fr 17; July 2026 Mo 20 to July 2026 Fr 24; July 2026 Mo 27 to July 2026 Fr 31; August 2026 Mo 3 to August 2026 Fr 7; August 2026 Mo 10 to August 2026 Fr 14; August 2026 Mo 17 to August 2026 Sa 22; August 2026 Mo 24 to August 2026 Fr 28; August 2026 Mo 31 to September 2026 Fr 4; September 2026 Mo 7 to September 2026 Fr 11; September 2026 Mo 14 to September 2026 Fr 18; September 2026 Mo 21 to September 2026 Fr 25; September 2026 Mo 28 to October 2026 Fr 2; October 2026 Mo 5 to October 2026 Fr 9; October 2026 Mo 12 to October 2026 Fr 16; October 2026 Mo 19 to October 2026 Fr 23; October 2026 Mo 26 to October 2026 Fr 30; November 2026 Mo 2 to November 2026 Fr 6; November 2026 Mo 9 to November 2026 Fr 13; November 2026 Mo 16 to November 2026 Fr 20; November 2026 Mo 23 to November 2026 Fr 27; November 2026 Mo 30 to December 2026 Fr 4; December 2026 Mo 7 to December 2026 Fr 11; December 2026 Mo 14 to December 2026 Fr 18; December 2026 Mo 21 to December 2026 Fr 25; December 2026 Mo 28 to December 2026 Th 31
── PHASE 4 — GROWTH & ANALYTICS
Analytics dashboard (sessions/conv) | Phase 4 | FE Dev | Planned | bar: June 2026 Mo 1 to June 2026 Fr 5; June 2026 Tu 9 to June 2026 Fr 12; June 2026 Mo 15 to June 2026 Fr 19; June 2026 Mo 22 to June 2026 Fr 26; June 2026 Mo 29 to July 2026 Fr 3; July 2026 Mo 6 to July 2026 Fr 10; July 2026 Mo 13 to July 2026 Fr 17; July 2026 Mo 20 to July 2026 Fr 24; July 2026 Mo 27 to July 2026 Fr 31; August 2026 Mo 3 to August 2026 Fr 7; August 2026 Mo 10 to August 2026 Fr 14; August 2026 Mo 17 to August 2026 Fr 21; August 2026 Mo 24 to August 2026 Fr 28; August 2026 Mo 31 to September 2026 Fr 4; September 2026 Mo 7 to September 2026 Fr 11; September 2026 Mo 14 to September 2026 Fr 18; September 2026 Mo 21 to September 2026 Fr 25; September 2026 Mo 28 to October 2026 Fr 2; October 2026 Mo 5 to October 2026 Fr 9; October 2026 Mo 12 to October 2026 Fr 16; October 2026 Mo 19 to October 2026 Fr 23; October 2026 Mo 26 to October 2026 Fr 30; November 2026 Mo 2 to November 2026 Fr 6; November 2026 Mo 9 to November 2026 Fr 13; November 2026 Mo 16 to November 2026 Fr 20; November 2026 Mo 23 to November 2026 Fr 27; November 2026 Mo 30 to December 2026 Fr 4; December 2026 Mo 7 to December 2026 Fr 11; December 2026 Mo 14 to December 2026 Fr 18; December 2026 Mo 21 to December 2026 Fr 25; December 2026 Mo 28 to December 2026 Th 31
Intent heatmap widget | Phase 4 | AI Engineer | Planned | bar: June 2026 Mo 1 to June 2026 Fr 5; June 2026 Tu 9 to June 2026 Fr 12; June 2026 Mo 15 to June 2026 Fr 19; June 2026 Mo 22 to June 2026 Fr 26; June 2026 Mo 29 to July 2026 Fr 3; July 2026 Mo 6 to July 2026 Fr 10; July 2026 Mo 13 to July 2026 Fr 17; July 2026 Mo 20 to July 2026 Fr 24; July 2026 Mo 27 to July 2026 Fr 31; August 2026 Mo 3 to August 2026 Fr 7; August 2026 Mo 10 to August 2026 Fr 14; August 2026 Mo 17 to August 2026 Fr 21; August 2026 Mo 24 to August 2026 Fr 28; August 2026 Mo 31 to September 2026 Fr 4; September 2026 Mo 7 to September 2026 Fr 11; September 2026 Mo 14 to September 2026 Fr 18; September 2026 Mo 21 to September 2026 Fr 25; September 2026 Mo 28 to October 2026 Fr 2; October 2026 Mo 5 to October 2026 Fr 9; October 2026 Mo 12 to October 2026 Fr 16; October 2026 Mo 19 to October 2026 Fr 23; October 2026 Mo 26 to October 2026 Fr 30; November 2026 Mo 2 to November 2026 Fr 6; November 2026 Mo 9 to November 2026 Fr 13; November 2026 Mo 16 to November 2026 Fr 20; November 2026 Mo 23 to November 2026 Fr 27; November 2026 Mo 30 to December 2026 Fr 4; December 2026 Mo 7 to December 2026 Fr 11; December 2026 Mo 14 to December 2026 Fr 18; December 2026 Mo 21 to December 2026 Fr 25; December 2026 Mo 28 to December 2026 Th 31
LINE OA + FB Messenger webhook | Phase 4 | Full-Stack Lead | Planned | bar: June 2026 Mo 1 to June 2026 Fr 5; June 2026 Tu 9 to June 2026 Fr 12; June 2026 Mo 15 to June 2026 Fr 19; June 2026 Mo 22 to June 2026 Fr 26; June 2026 Mo 29 to July 2026 Fr 3; July 2026 Mo 6 to July 2026 Fr 10; July 2026 Mo 13 to July 2026 Fr 17; July 2026 Mo 20 to July 2026 Fr 24; July 2026 Mo 27 to July 2026 Fr 31; August 2026 Mo 3 to August 2026 Fr 7; August 2026 Mo 10 to August 2026 Fr 14; August 2026 Mo 17 to August 2026 Fr 21; August 2026 Mo 24 to August 2026 Fr 28; August 2026 Mo 31 to September 2026 Fr 4; September 2026 Mo 7 to September 2026 Fr 11; September 2026 Mo 14 to September 2026 Fr 18; September 2026 Mo 21 to September 2026 Fr 25; September 2026 Mo 28 to October 2026 Fr 2; October 2026 Mo 5 to October 2026 Fr 9; October 2026 Mo 12 to October 2026 Fr 16; October 2026 Mo 19 to October 2026 Fr 23; October 2026 Mo 26 to October 2026 Fr 30; November 2026 Mo 2 to November 2026 Fr 6; November 2026 Mo 9 to November 2026 Fr 13; November 2026 Mo 16 to November 2026 Fr 20; November 2026 Mo 23 to November 2026 Fr 27; November 2026 Mo 30 to December 2026 Fr 4; December 2026 Mo 7 to December 2026 Fr 11; December 2026 Mo 14 to December 2026 Fr 18; December 2026 Mo 21 to December 2026 Fr 25; December 2026 Mo 28 to December 2026 Th 31
Enterprise tier + custom domain | Phase 4 | Full-Stack Lead | Planned | bar: June 2026 Mo 1 to June 2026 Fr 5; June 2026 Tu 9 to June 2026 Fr 12; June 2026 Mo 15 to June 2026 Fr 19; June 2026 Mo 22 to June 2026 Fr 26; June 2026 Mo 29 to July 2026 Fr 3; July 2026 Mo 6 to July 2026 Fr 10; July 2026 Mo 13 to July 2026 Fr 17; July 2026 Mo 20 to July 2026 Fr 24; July 2026 Mo 27 to July 2026 Fr 31; August 2026 Mo 3 to August 2026 Fr 7; August 2026 Mo 10 to August 2026 Fr 14; August 2026 Mo 17 to August 2026 Fr 21; August 2026 Mo 24 to August 2026 Fr 28; August 2026 Mo 31 to September 2026 Fr 4; September 2026 Mo 7 to September 2026 Fr 11; September 2026 Mo 14 to September 2026 Fr 18; September 2026 Mo 21 to September 2026 Fr 25; September 2026 Mo 28 to October 2026 Fr 2; October 2026 Mo 5 to October 2026 Fr 9; October 2026 Mo 12 to October 2026 Fr 16; October 2026 Mo 19 to October 2026 Fr 23; October 2026 Mo 26 to October 2026 Fr 30; November 2026 Mo 2 to November 2026 Fr 6; November 2026 Mo 9 to November 2026 Fr 13; November 2026 Mo 16 to November 2026 Fr 20; November 2026 Mo 23 to November 2026 Fr 27; November 2026 Mo 30 to December 2026 Fr 4; December 2026 Mo 7 to December 2026 Fr 11; December 2026 Mo 14 to December 2026 Fr 18; December 2026 Mo 21 to December 2026 Fr 25; December 2026 Mo 28 to December 2026 Th 31
A/B testing hooks for widget | Phase 4 | Widget Eng | Planned | bar: June 2026 Mo 1 to June 2026 Fr 5; June 2026 Tu 9 to June 2026 Fr 12; June 2026 Mo 15 to June 2026 Fr 19; June 2026 Mo 22 to June 2026 Fr 26; June 2026 Mo 29 to July 2026 Fr 3; July 2026 Mo 6 to July 2026 Fr 10; July 2026 Mo 13 to July 2026 Fr 17; July 2026 Mo 20 to July 2026 Fr 24; July 2026 Mo 27 to July 2026 Fr 31; August 2026 Mo 3 to August 2026 Fr 7; August 2026 Mo 10 to August 2026 Fr 14; August 2026 Mo 17 to August 2026 Fr 21; August 2026 Mo 24 to August 2026 Fr 28; August 2026 Mo 31 to September 2026 Fr 4; September 2026 Mo 7 to September 2026 Fr 11; September 2026 Mo 14 to September 2026 Fr 18; September 2026 Mo 21 to September 2026 Fr 25; September 2026 Mo 28 to October 2026 Fr 2; October 2026 Mo 5 to October 2026 Fr 9; October 2026 Mo 12 to October 2026 Fr 16; October 2026 Mo 19 to October 2026 Fr 23; October 2026 Mo 26 to October 2026 Fr 30; November 2026 Mo 2 to November 2026 Fr 6; November 2026 Mo 9 to November 2026 Fr 13; November 2026 Mo 16 to November 2026 Fr 20; November 2026 Mo 23 to November 2026 Fr 27; November 2026 Mo 30 to December 2026 Fr 4; December 2026 Mo 7 to December 2026 Fr 11; December 2026 Mo 14 to December 2026 Fr 18; December 2026 Mo 21 to December 2026 Fr 25; December 2026 Mo 28 to December 2026 Th 31
Phase 4 QA + UAT | Phase 4 | QA | Planned | bar: June 2026 Mo 1 to June 2026 Fr 5; June 2026 Tu 9 to June 2026 Fr 12; June 2026 Mo 15 to June 2026 Fr 19; June 2026 Mo 22 to June 2026 Fr 26; June 2026 Mo 29 to July 2026 Fr 3; July 2026 Mo 6 to July 2026 Fr 10; July 2026 Mo 13 to July 2026 Fr 17; July 2026 Mo 20 to July 2026 Fr 24; July 2026 Mo 27 to July 2026 Fr 31; August 2026 Mo 3 to August 2026 Fr 7; August 2026 Mo 10 to August 2026 Fr 14; August 2026 Mo 17 to August 2026 Fr 21; August 2026 Mo 24 to August 2026 Fr 28; August 2026 Mo 31 to September 2026 Fr 4; September 2026 Mo 7 to September 2026 Fr 11; September 2026 Mo 14 to September 2026 Fr 18; September 2026 Mo 21 to September 2026 Fr 25; September 2026 Mo 28 to October 2026 Fr 2; October 2026 Mo 5 to October 2026 Fr 9; October 2026 Mo 12 to October 2026 Fr 16; October 2026 Mo 19 to October 2026 Fr 23; October 2026 Mo 26 to October 2026 Fr 30; November 2026 Mo 2 to November 2026 Fr 6; November 2026 Mo 9 to November 2026 Fr 13; November 2026 Mo 16 to November 2026 Fr 20; November 2026 Mo 23 to November 2026 Fr 27; November 2026 Mo 30 to December 2026 Fr 4; December 2026 Mo 7 to December 2026 Fr 11; December 2026 Mo 14 to December 2026 Fr 18; December 2026 Mo 21 to December 2026 Fr 25; December 2026 Mo 28 to December 2026 Th 31
★ Phase 4 Milestone |  |  | Oct 31 | bar: June 2026 Mo 1 to June 2026 Fr 5; June 2026 Tu 9 to June 2026 Fr 12; June 2026 Mo 15 to June 2026 Fr 19; June 2026 Mo 22 to June 2026 Fr 26; June 2026 Mo 29 to July 2026 Fr 3; July 2026 Mo 6 to July 2026 Fr 10; July 2026 Mo 13 to July 2026 Fr 17; July 2026 Mo 20 to July 2026 Fr 24; July 2026 Mo 27 to July 2026 Fr 31; August 2026 Mo 3 to August 2026 Fr 7; August 2026 Mo 10 to August 2026 Fr 14; August 2026 Mo 17 to August 2026 Fr 21; August 2026 Mo 24 to August 2026 Fr 28; August 2026 Mo 31 to September 2026 Fr 4; September 2026 Mo 7 to September 2026 Fr 11; September 2026 Mo 14 to September 2026 Fr 18; September 2026 Mo 21 to September 2026 Fr 25; September 2026 Mo 28 to October 2026 Fr 2; October 2026 Mo 5 to October 2026 Fr 9; October 2026 Mo 12 to October 2026 Fr 16; October 2026 Mo 19 to October 2026 Fr 23; October 2026 Mo 26 to October 2026 Sa 31; November 2026 Mo 2 to November 2026 Fr 6; November 2026 Mo 9 to November 2026 Fr 13; November 2026 Mo 16 to November 2026 Fr 20; November 2026 Mo 23 to November 2026 Fr 27; November 2026 Mo 30 to December 2026 Fr 4; December 2026 Mo 7 to December 2026 Fr 11; December 2026 Mo 14 to December 2026 Fr 18; December 2026 Mo 21 to December 2026 Fr 25; December 2026 Mo 28 to December 2026 Th 31
── v2.0 GA — LAUNCH PREPARATION
Production hardening (rate limit/WAF) | v2.0 GA | DevOps | Planned | bar: June 2026 Mo 1 to June 2026 Fr 5; June 2026 Tu 9 to June 2026 Fr 12; June 2026 Mo 15 to June 2026 Fr 19; June 2026 Mo 22 to June 2026 Fr 26; June 2026 Mo 29 to July 2026 Fr 3; July 2026 Mo 6 to July 2026 Fr 10; July 2026 Mo 13 to July 2026 Fr 17; July 2026 Mo 20 to July 2026 Fr 24; July 2026 Mo 27 to July 2026 Fr 31; August 2026 Mo 3 to August 2026 Fr 7; August 2026 Mo 10 to August 2026 Fr 14; August 2026 Mo 17 to August 2026 Fr 21; August 2026 Mo 24 to August 2026 Fr 28; August 2026 Mo 31 to September 2026 Fr 4; September 2026 Mo 7 to September 2026 Fr 11; September 2026 Mo 14 to September 2026 Fr 18; September 2026 Mo 21 to September 2026 Fr 25; September 2026 Mo 28 to October 2026 Fr 2; October 2026 Mo 5 to October 2026 Fr 9; October 2026 Mo 12 to October 2026 Fr 16; October 2026 Mo 19 to October 2026 Fr 23; October 2026 Mo 26 to October 2026 Fr 30; November 2026 Mo 2 to November 2026 Fr 6; November 2026 Mo 9 to November 2026 Fr 13; November 2026 Mo 16 to November 2026 Fr 20; November 2026 Mo 23 to November 2026 Fr 27; November 2026 Mo 30 to December 2026 Fr 4; December 2026 Mo 7 to December 2026 Fr 11; December 2026 Mo 14 to December 2026 Fr 18; December 2026 Mo 21 to December 2026 Fr 25; December 2026 Mo 28 to December 2026 Th 31
Partner affiliate programme live | v2.0 GA | Full-Stack Lead | Planned | bar: June 2026 Mo 1 to June 2026 Fr 5; June 2026 Tu 9 to June 2026 Fr 12; June 2026 Mo 15 to June 2026 Fr 19; June 2026 Mo 22 to June 2026 Fr 26; June 2026 Mo 29 to July 2026 Fr 3; July 2026 Mo 6 to July 2026 Fr 10; July 2026 Mo 13 to July 2026 Fr 17; July 2026 Mo 20 to July 2026 Fr 24; July 2026 Mo 27 to July 2026 Fr 31; August 2026 Mo 3 to August 2026 Fr 7; August 2026 Mo 10 to August 2026 Fr 14; August 2026 Mo 17 to August 2026 Fr 21; August 2026 Mo 24 to August 2026 Fr 28; August 2026 Mo 31 to September 2026 Fr 4; September 2026 Mo 7 to September 2026 Fr 11; September 2026 Mo 14 to September 2026 Fr 18; September 2026 Mo 21 to September 2026 Fr 25; September 2026 Mo 28 to October 2026 Fr 2; October 2026 Mo 5 to October 2026 Fr 9; October 2026 Mo 12 to October 2026 Fr 16; October 2026 Mo 19 to October 2026 Fr 23; October 2026 Mo 26 to October 2026 Fr 30; November 2026 Mo 2 to November 2026 Fr 6; November 2026 Mo 9 to November 2026 Fr 13; November 2026 Mo 16 to November 2026 Fr 20; November 2026 Mo 23 to November 2026 Fr 27; November 2026 Mo 30 to December 2026 Fr 4; December 2026 Mo 7 to December 2026 Fr 11; December 2026 Mo 14 to December 2026 Fr 18; December 2026 Mo 21 to December 2026 Fr 25; December 2026 Mo 28 to December 2026 Th 31
All packages live on landing | v2.0 GA | FE Dev | Planned | bar: June 2026 Mo 1 to June 2026 Fr 5; June 2026 Tu 9 to June 2026 Fr 12; June 2026 Mo 15 to June 2026 Fr 19; June 2026 Mo 22 to June 2026 Fr 26; June 2026 Mo 29 to July 2026 Fr 3; July 2026 Mo 6 to July 2026 Fr 10; July 2026 Mo 13 to July 2026 Fr 17; July 2026 Mo 20 to July 2026 Fr 24; July 2026 Mo 27 to July 2026 Fr 31; August 2026 Mo 3 to August 2026 Fr 7; August 2026 Mo 10 to August 2026 Fr 14; August 2026 Mo 17 to August 2026 Fr 21; August 2026 Mo 24 to August 2026 Fr 28; August 2026 Mo 31 to September 2026 Fr 4; September 2026 Mo 7 to September 2026 Fr 11; September 2026 Mo 14 to September 2026 Fr 18; September 2026 Mo 21 to September 2026 Fr 25; September 2026 Mo 28 to October 2026 Fr 2; October 2026 Mo 5 to October 2026 Fr 9; October 2026 Mo 12 to October 2026 Fr 16; October 2026 Mo 19 to October 2026 Fr 23; October 2026 Mo 26 to October 2026 Fr 30; November 2026 Mo 2 to November 2026 Fr 6; November 2026 Mo 9 to November 2026 Fr 13; November 2026 Mo 16 to November 2026 Fr 20; November 2026 Mo 23 to November 2026 Fr 27; November 2026 Mo 30 to December 2026 Fr 4; December 2026 Mo 7 to December 2026 Fr 11; December 2026 Mo 14 to December 2026 Fr 18; December 2026 Mo 21 to December 2026 Fr 25; December 2026 Mo 28 to December 2026 Th 31
Full regression + pen test | v2.0 GA | QA + DevOps | Planned | bar: June 2026 Mo 1 to June 2026 Fr 5; June 2026 Tu 9 to June 2026 Fr 12; June 2026 Mo 15 to June 2026 Fr 19; June 2026 Mo 22 to June 2026 Fr 26; June 2026 Mo 29 to July 2026 Fr 3; July 2026 Mo 6 to July 2026 Fr 10; July 2026 Mo 13 to July 2026 Fr 17; July 2026 Mo 20 to July 2026 Fr 24; July 2026 Mo 27 to July 2026 Fr 31; August 2026 Mo 3 to August 2026 Fr 7; August 2026 Mo 10 to August 2026 Fr 14; August 2026 Mo 17 to August 2026 Fr 21; August 2026 Mo 24 to August 2026 Fr 28; August 2026 Mo 31 to September 2026 Fr 4; September 2026 Mo 7 to September 2026 Fr 11; September 2026 Mo 14 to September 2026 Fr 18; September 2026 Mo 21 to September 2026 Fr 25; September 2026 Mo 28 to October 2026 Fr 2; October 2026 Mo 5 to October 2026 Fr 9; October 2026 Mo 12 to October 2026 Fr 16; October 2026 Mo 19 to October 2026 Fr 23; October 2026 Mo 26 to October 2026 Fr 30; November 2026 Mo 2 to November 2026 Fr 6; November 2026 Mo 9 to November 2026 Fr 13; November 2026 Mo 16 to November 2026 Fr 20; November 2026 Mo 23 to November 2026 Fr 27; November 2026 Mo 30 to December 2026 Fr 4; December 2026 Mo 7 to December 2026 Fr 11; December 2026 Mo 14 to December 2026 Fr 18; December 2026 Mo 21 to December 2026 Fr 25; December 2026 Mo 28 to December 2026 Th 31
Uptime SLA setup + monitoring | v2.0 GA | DevOps | Planned | bar: June 2026 Mo 1 to June 2026 Fr 5; June 2026 Tu 9 to June 2026 Fr 12; June 2026 Mo 15 to June 2026 Fr 19; June 2026 Mo 22 to June 2026 Fr 26; June 2026 Mo 29 to July 2026 Fr 3; July 2026 Mo 6 to July 2026 Fr 10; July 2026 Mo 13 to July 2026 Fr 17; July 2026 Mo 20 to July 2026 Fr 24; July 2026 Mo 27 to July 2026 Fr 31; August 2026 Mo 3 to August 2026 Fr 7; August 2026 Mo 10 to August 2026 Fr 14; August 2026 Mo 17 to August 2026 Fr 21; August 2026 Mo 24 to August 2026 Fr 28; August 2026 Mo 31 to September 2026 Fr 4; September 2026 Mo 7 to September 2026 Fr 11; September 2026 Mo 14 to September 2026 Fr 18; September 2026 Mo 21 to September 2026 Fr 25; September 2026 Mo 28 to October 2026 Fr 2; October 2026 Mo 5 to October 2026 Fr 9; October 2026 Mo 12 to October 2026 Fr 16; October 2026 Mo 19 to October 2026 Fr 23; October 2026 Mo 26 to October 2026 Fr 30; November 2026 Mo 2 to November 2026 Fr 6; November 2026 Mo 9 to November 2026 Fr 13; November 2026 Mo 16 to November 2026 Fr 20; November 2026 Mo 23 to November 2026 Fr 27; November 2026 Mo 30 to December 2026 Fr 4; December 2026 Mo 7 to December 2026 Fr 11; December 2026 Mo 14 to December 2026 Fr 18; December 2026 Mo 21 to December 2026 Fr 25; December 2026 Mo 28 to December 2026 Th 31
★★ v2.0 GA LAUNCH |  |  | Dec 31 | bar: June 2026 Mo 1 to June 2026 Fr 5; June 2026 Tu 9 to June 2026 Fr 12; June 2026 Mo 15 to June 2026 Fr 19; June 2026 Mo 22 to June 2026 Fr 26; June 2026 Mo 29 to July 2026 Fr 3; July 2026 Mo 6 to July 2026 Fr 10; July 2026 Mo 13 to July 2026 Fr 17; July 2026 Mo 20 to July 2026 Fr 24; July 2026 Mo 27 to July 2026 Fr 31; August 2026 Mo 3 to August 2026 Fr 7; August 2026 Mo 10 to August 2026 Fr 14; August 2026 Mo 17 to August 2026 Fr 21; August 2026 Mo 24 to August 2026 Fr 28; August 2026 Mo 31 to September 2026 Fr 4; September 2026 Mo 7 to September 2026 Fr 11; September 2026 Mo 14 to September 2026 Fr 18; September 2026 Mo 21 to September 2026 Fr 25; September 2026 Mo 28 to October 2026 Fr 2; October 2026 Mo 5 to October 2026 Fr 9; October 2026 Mo 12 to October 2026 Fr 16; October 2026 Mo 19 to October 2026 Fr 23; October 2026 Mo 26 to October 2026 Fr 30; November 2026 Mo 2 to November 2026 Fr 6; November 2026 Mo 9 to November 2026 Fr 13; November 2026 Mo 16 to November 2026 Fr 20; November 2026 Mo 23 to November 2026 Fr 27; November 2026 Mo 30 to December 2026 Fr 4; December 2026 Mo 7 to December 2026 Fr 11; December 2026 Mo 14 to December 2026 Fr 18; December 2026 Mo 21 to December 2026 Fr 25; December 2026 Mo 28 to December 2026 Th 31

## Objectives
# | Objective | Key Deliverable | Status
O1 | Production-ready AI sales agent for Thai SMEs | Zudobot SaaS v1.0 (web + API + widget) | Done (Phase 1)
O2 | Tenant self-service onboarding with Google OAuth | Onboarding flow, dashboard, billing checkout | Done (Phase 1)
O3 | Embeddable chat widget for client storefronts | widget.js — PDPA consent + product cards + file attach | Stabilising
O4 | Comply with Thai PDPA and GDPR | Data export/delete, consent audit trail, 2FA | Done (Phase 2)
O5 | Launch monetisable ReadyPackage pricing system | CostPriceScenario + ReadyPackage + /checkout | Done
O6 | Partner portal with commission programme | Partner Google Auth, earn-rate config, affiliate tracking | Phase 3 – Planned
O7 | Growth analytics and third-party integrations | Analytics dashboard, LINE OA, Facebook Messenger | Phase 4 – Planned
O8 | v2.0 General Availability launch | Production hardening, uptime SLA, all packages live | Dec 2026 – Planned

## Roles
Role | Responsibilities | Owner (Example) | Primary Apps
Product Owner | Feature priorities, business decisions, ReadyPackage pricing rules, go/no-go for releases | Founder (Luesat) | All
Full-Stack Lead | Architecture, API design, code review, DB schema, CostPriceScenario engine, auth flows | Senior Dev | apps/api, apps/web
Frontend Dev | Dashboard UI, landing page, checkout flow, admin panels, i18n (EN+TH) | FE Dev | apps/web, apps/landing
Widget Engineer | packages/widget — file attachment, identity memory, typing delay, Constitutional AI rules | Widget Specialist | packages/widget
AI / ML Engineer | Gemini prompt engineering, Constitutional AI sections F+G, product embedding, intent detection | AI Engineer | apps/api (Gemini layer)
QA Engineer | Manual + automated tests, mobile regression, PDPA consent validation, Deep Link tests | QA | All
DevOps | Amplify CI/CD, MongoDB Atlas, CDN for widget.js, env secrets, uptime monitoring | DevOps | Infra / CI
Legal / Compliance | PDPA/GDPR review, WHT accounting rules (backend-only), Terms of Service, privacy page copy | Legal Advisor | Policy docs

## Risk Register
# | Risk | Likelihood | Impact | Mitigation Strategy | Owner
R1 | Gemini API pricing change or quota limit | Medium | High | Cache responses, fallback prompt truncation, token usage alerts per tenant on Google Cloud | AI Eng + DevOps
R2 | PDPA non-compliance — consent not recorded | Low | Critical | Widget blocks chat until consentAt written to DB; consent stored in localStorage + API confirmed | Full-Stack + Legal
R3 | WHT shown to customers in checkout UI | Low | High | WHT is backend-only; checkout summary never renders WHT line; code-review gate on checkout UI changes | Full-Stack + Legal
R4 | Google OAuth token revoked mid-session | Medium | Medium | NextAuth session refresh every 15 min; graceful /login redirect; preserve form data in sessionStorage | Full-Stack Lead
R5 | MongoDB Atlas outage | Low | Critical | Multi-region replica set; read preference secondaryPreferred; 6h automated backup; health-check alert | DevOps
R6 | Widget script blocked by client CSP | Medium | Medium | Document required CSP headers in onboarding guide; provide nonce-compatible build for enterprise | Widget Eng
R7 | Competitor price undercut | Medium | Medium | ReadyPackage dual-gate (isActive + isOnSale) enables instant promo without code deploy | Product Owner
R8 | Data breach — email hash or session token | Low | Critical | Store only SHA-256 hash; 10-min TTL on Deep Link tokens; audit log on every GDPR delete call | Full-Stack + DevOps
R9 | Scope creep delaying GA launch | High | Medium | Strict phase gate: unapproved features go to next sprint; PO has final say on mid-sprint additions | Product Owner
R10 | Thai PDPA legal text mistranslation | Medium | High | Native Thai speaker reviews all consent copy; legal advisor signs off privacy page before deploy | Legal + QA

## Communication Plan
Type | Channel | Cadence | Audience | Purpose
INTERNAL | Daily Stand-up (LINE / Slack) | Daily 09:00 | All devs | Blockers, yesterday / today progress
INTERNAL | Sprint Review (Google Meet) | Bi-weekly Friday | All team + PO | Demo completed features, adjust backlog priority
INTERNAL | Architecture Decision (GitHub) | As needed | Tech leads | Record ADRs: DB schema, API contract, Gemini model version
INTERNAL | Bug Triage (Linear) | Monday | QA + FE + BE | Prioritise regression bugs vs new feature work
INTERNAL | Finance / Pricing Review | Monthly | PO + Legal | CostPriceScenario updates, margin review, WHT compliance
INTERNAL | Security & Compliance Review | Quarterly | Full-Stack + Legal + DevOps | PDPA audit trail, 2FA adoption rate, token rotation review
EXTERNAL | Landing page /changelog | Per release | All users (public) | Feature announcements, pricing changes, new packages
EXTERNAL | LINE Notify alerts | On trigger | Tenant users | Live chat handoff notification, Deep Link token delivery
EXTERNAL | Email via Resend | On event | Registered tenants | Onboarding, billing receipts, renewal reminders, 2FA setup
EXTERNAL | Partner Newsletter | Monthly | Active partners | Commission reports, new ReadyPackage availability, promos
EXTERNAL | Status Page | Continuous | All users | Uptime monitoring, planned maintenance, incident updates
EXTERNAL | In-widget admin broadcast | On admin push | Widget end-users | Feature highlights, promotions, store announcements
EXTERNAL | Support chat / email | On demand | Any user | Bug reports, billing questions, onboarding help